## Q2 Gantt - Arthur
ARTHUR ¦ Q2 2026 Marketing Plan ¦ April - June ¦ Prepared by Kitto
|  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026
Workstream / Task | Owner | 1 Apr | 8 Apr | 15 Apr | 22 Apr | 29 Apr | 6 May | 13 May | 20 May | 27 May | 3 Jun | 10 Jun | 17 Jun | 24 Jun
01 / Website Launch & Phase 2
Compile content day assets & prep launch [26 Mar content day feeds this] | Kitto
Coordinated launch campaign (LinkedIn + site go-live) [Target: w/c 6 Apr] | Kitto + All
Sector page content write-up | Kitto
Candidate Career Pathway Landing Pages | Kitto
Salary CTA + consultation booking flow | Kitto
Case study pages published (ongoing) [Feeds from WS02] | Kitto
02 / Case Study Programme
Interview framework + consultant outreach | Kitto
George Hudson interview + CS write-up (x2) | Kitto + George
Consultant interviews - practice areas 1-3 | Kitto
CS write-ups batch 1 (PDF + web) | Kitto
Consultant interviews - practice areas 4-6 | Kitto
CS write-ups batch 2 + shared resource build | Kitto
03 / Sector Marketing Packs
Template suite design (deck, salary snapshot, insight) | Kitto
Priority packs 1-5 (top billing areas) [Consultant salary data needed] | Kitto
Packs 6-12 - remaining practice areas | Kitto
Shared folder structure + consultant rollout | Kitto + Lizel
04 / Director LinkedIn Programme
Profile audits + optimisation (all 4 directors) | Kitto
90-day content plans per director [Needs director sign-off] | Kitto
Simon Caplan - Content Calls | Kitto + Simon
George Hudson - Content Calls | Kitto + George
Dan / William - Content Calls | Kitto + Dan/Will
Monthly reach / ICP engagement review | Kitto + Lizel
05 / Product GTM
Product positioning docs (all 4 lines) | Kitto
Arthur Container GTM deck (priority) [Highest commercial priority] | Kitto
Product one-pagers (PDF + web copy) | Kitto
Website product pages live | Kitto
Email outreach sequence per product | Kitto
06 / Always-On Social Content
Monthly content calendar - April [3 posts/week min] | Kitto
Company page publishing - April | Kitto
Monthly content calendar - May | Kitto
Company page publishing - May | Kitto
Monthly content calendar - June | Kitto
Company page publishing - June | Kitto
Consultant insight post drafts (monthly, all) | Kitto
Monthly content performance review | Kitto + Lizel
07 / Talent Attraction Campaign
Review TA materials from Amity (stories, EVP content) | Kitto
Brochure copy & design [Content day assets feed this] | Kitto
Careers page imagery update [Swap stock post-content day] | Kitto
Present brochure draft to Zoe [Zoe back w/c 13 Apr] | Kitto + Zoe |  |  | ▲
Brochure revisions + final sign-off | Kitto + Zoe
LinkedIn TA content pack for Zoe [Post templates, outreach messaging] | Kitto
Ongoing TA LinkedIn content + Zoe outreach support | Kitto + Zoe
KEY MILESTONES |  |  | ▲ Website Launch | ▲ Brochure v1 to Zoe |  |  | ▲ Sector Packs 1-5 Done |  |  | ▲ Case Studies Published |  |  |  | ▲ Q2 Review
COLOUR KEY: |  | 01 Website Launch |  | 02 Case Studies |  | 03 Sector Packs |  | 04 Director LinkedIn |  | 05 Product GTM |  | 06 Social Content |  | 07 TA Campaign